## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
Task | Screen/Function | Feature | Actor | Screen/Function Description | Complexity | In Charge | Status | Update Details | Priority
BE-01 | Register / Login | Register account — API | Storage Customer | Sign-up form for name, email, phone and password. Validates the input and sends a verification email before the account can be used. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, Role. | Medium | Khang | To Do |  | Core
FE-01 | Register / Login | Register account — UI | Storage Customer | Sign-up form for name, email, phone and password. Validates the input and sends a verification email before the account can be used. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-02 | Register / Login | Email verification — API | Storage Customer | Confirms a new account from the token link in the email and activates it. Expired tokens can be re-sent. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, Role. | Simple | Khang | To Do |  | Core
FE-02 | Register / Login | Email verification — UI | Storage Customer | Confirms a new account from the token link in the email and activates it. Expired tokens can be re-sent. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Core
BE-03 | Register / Login | Login — API | Storage Customer | Pop-up screen for email and password, with links to register and to reset a forgotten password. Issues the session token on success. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, Role. | Medium | Khang | To Do |  | Core
FE-03 | Register / Login | Login — UI | Storage Customer | Pop-up screen for email and password, with links to register and to reset a forgotten password. Issues the session token on success. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-04 | Register / Login | Forgot / reset password — API | Storage Customer | Sends a one-time reset link to the registered email and lets the customer set a new password. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, Role. | Medium | Khang | To Do |  | Supporting
FE-04 | Register / Login | Forgot / reset password — UI | Storage Customer | Sends a one-time reset link to the registered email and lets the customer set a new password. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-05 | Admin Login | Staff login — API | Facility Staff, Facility Manager, System Administrator | Sign-in for staff accounts, redirecting to the right workspace based on the account's role. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, Role. | Medium | Khang | To Do |  | Core
FE-05 | Admin Login | Staff login — UI | Facility Staff, Facility Manager, System Administrator | Sign-in for staff accounts, redirecting to the right workspace based on the account's role. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-06 | Facility Search | Search & filter facilities — API | Storage Customer | Lists facilities filtered by district, unit size and price range, with sorting by price and distance. ▸ Backend: endpoints, service logic, validation and role check. Tables: Facility, StorageUnit, UnitType. | Medium | Khang | To Do |  | Core
FE-06 | Facility Search | Search & filter facilities — UI | Storage Customer | Lists facilities filtered by district, unit size and price range, with sorting by price and distance. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-07 | Facility Search | Facility detail — API | Storage Customer | Shows one facility: address, opening hours, photos, security features and the unit types available there. ▸ Backend: endpoints, service logic, validation and role check. Tables: Facility, StorageUnit, UnitType. | Medium | Khang | To Do |  | Core
FE-07 | Facility Search | Facility detail — UI | Storage Customer | Shows one facility: address, opening hours, photos, security features and the unit types available there. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-08 | Unit Catalog | Unit type list & size guide — API | Storage Customer | Lists unit types with area and dimensions and a visual size guide showing what fits in each. ▸ Backend: endpoints, service logic, validation and role check. Tables: UnitType, StorageUnit, UnitPrice. | Simple | Trường | To Do |  | Core
FE-08 | Unit Catalog | Unit type list & size guide — UI | Storage Customer | Lists unit types with area and dimensions and a visual size guide showing what fits in each. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Core
BE-09 | Unit Catalog | Availability check — API | Storage Customer | Shows how many units of each type are free at a facility for the chosen move-in date, excluding units already held. ▸ Backend: endpoints, service logic, validation and role check. Tables: UnitType, StorageUnit, UnitPrice. | Complex | Trường | To Do |  | Core
FE-09 | Unit Catalog | Availability check — UI | Storage Customer | Shows how many units of each type are free at a facility for the chosen move-in date, excluding units already held. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-10 | Unit Catalog | Price quote — API | Storage Customer | Calculates monthly rent, deposit and applicable fees from the pricing policy in force on the move-in date. ▸ Backend: endpoints, service logic, validation and role check. Tables: UnitType, StorageUnit, UnitPrice. | Complex | Trường | To Do |  | Core
FE-10 | Unit Catalog | Price quote — UI | Storage Customer | Calculates monthly rent, deposit and applicable fees from the pricing policy in force on the move-in date. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-11 | Unit Type & Pricing | Unit type CRUD — API | Business Operations Manager | Manages unit types with code, area and dimensions. ▸ Backend: endpoints, service logic, validation and role check. Tables: UnitType, PricingPolicy, UnitPrice, FeeType. | Simple | Trường | To Do |  | Core
FE-11 | Unit Type & Pricing | Unit type CRUD — UI | Business Operations Manager | Manages unit types with code, area and dimensions. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Thiện | To Do |  | Core
BE-12 | Unit Type & Pricing | Pricing policy versions — API | Business Operations Manager | Creates a new pricing policy version with an effective date; only one version may be active at a time. ▸ Backend: endpoints, service logic, validation and role check. Tables: UnitType, PricingPolicy, UnitPrice, FeeType. | Complex | Trường | To Do |  | Core
FE-12 | Unit Type & Pricing | Pricing policy versions — UI | Business Operations Manager | Creates a new pricing policy version with an effective date; only one version may be active at a time. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-13 | Unit Type & Pricing | Unit price table — API | Business Operations Manager | Sets the base monthly price for each unit type inside a pricing policy version. ▸ Backend: endpoints, service logic, validation and role check. Tables: UnitType, PricingPolicy, UnitPrice, FeeType. | Medium | Trường | To Do |  | Core
FE-13 | Unit Type & Pricing | Unit price table — UI | Business Operations Manager | Sets the base monthly price for each unit type inside a pricing policy version. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-14 | Unit Type & Pricing | Fee type setup — API | Business Operations Manager | Defines late fee, lock replacement fee and other charges with their amounts and rules. ▸ Backend: endpoints, service logic, validation and role check. Tables: UnitType, PricingPolicy, UnitPrice, FeeType. | Medium | Trường | To Do |  | Supporting
FE-14 | Unit Type & Pricing | Fee type setup — UI | Business Operations Manager | Defines late fee, lock replacement fee and other charges with their amounts and rules. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Supporting
BE-15 | Facility Management | Facility CRUD — API | System Administrator | Creates, edits and deactivates facilities with address, district, opening hours and photos. ▸ Backend: endpoints, service logic, validation and role check. Tables: Facility, Floor, StorageUnit. | Medium | Khang | To Do |  | Core
FE-15 | Facility Management | Facility CRUD — UI | System Administrator | Creates, edits and deactivates facilities with address, district, opening hours and photos. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-16 | Facility Management | Floor CRUD — API | System Administrator | Manages the floors inside a facility and their numbering. ▸ Backend: endpoints, service logic, validation and role check. Tables: Facility, Floor, StorageUnit. | Simple | Khang | To Do |  | Supporting
FE-16 | Facility Management | Floor CRUD — UI | System Administrator | Manages the floors inside a facility and their numbering. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Thiện | To Do |  | Supporting
BE-17 | Facility Management | Unit CRUD — API | Facility Manager | Creates and edits storage units with unit code, floor and unit type, in bulk or one by one. ▸ Backend: endpoints, service logic, validation and role check. Tables: Facility, Floor, StorageUnit. | Medium | Khang | To Do |  | Core
FE-17 | Facility Management | Unit CRUD — UI | Facility Manager | Creates and edits storage units with unit code, floor and unit type, in bulk or one by one. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-18 | Facility Management | Unit status board — API | Facility Staff, Facility Manager | Grid of every unit in a facility, colour-coded by status: available, reserved, occupied or under maintenance. ▸ Backend: endpoints, service logic, validation and role check. Tables: Facility, Floor, StorageUnit. | Complex | Khang | To Do |  | Core
FE-18 | Facility Management | Unit status board — UI | Facility Staff, Facility Manager | Grid of every unit in a facility, colour-coded by status: available, reserved, occupied or under maintenance. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-19 | Reservation | Create reservation — API | Storage Customer | Booking form for facility, unit type and move-in date. Holds a matching unit and creates the reservation in Pending status. ▸ Backend: endpoints, service logic, validation and role check. Tables: Reservation, StorageUnit, Invoice. | Complex | Khang | To Do |  | Core
FE-19 | Reservation | Create reservation — UI | Storage Customer | Booking form for facility, unit type and move-in date. Holds a matching unit and creates the reservation in Pending status. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Đạt | To Do |  | Core
BE-20 | Reservation | Deposit payment — API | Storage Customer | Sends the customer to the payment gateway for the deposit and records the result against the reservation. ▸ Backend: endpoints, service logic, validation and role check. Tables: Reservation, StorageUnit, Invoice. | Complex | Khang | To Do |  | Core
FE-20 | Reservation | Deposit payment — UI | Storage Customer | Sends the customer to the payment gateway for the deposit and records the result against the reservation. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Đạt | To Do |  | Core
BE-21 | Reservation | Reservation confirmation — API | Storage Customer | Confirmation screen with the reservation code, booking summary and what to bring on move-in day. ▸ Backend: endpoints, service logic, validation and role check. Tables: Reservation, StorageUnit, Invoice. | Simple | Khang | To Do |  | Core
FE-21 | Reservation | Reservation confirmation — UI | Storage Customer | Confirmation screen with the reservation code, booking summary and what to bring on move-in day. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Core
BE-22 | Reservation | My reservations — API | Storage Customer | Lists the customer's own reservations with status, and allows cancelling one before the move-in date. ▸ Backend: endpoints, service logic, validation and role check. Tables: Reservation, StorageUnit, Invoice. | Medium | Khang | To Do |  | Core
FE-22 | Reservation | My reservations — UI | Storage Customer | Lists the customer's own reservations with status, and allows cancelling one before the move-in date. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-23 | Reservation Management | Reservation queue — API | Facility Staff | Lists reservations by status with search by code, customer name, phone and move-in date. ▸ Backend: endpoints, service logic, validation and role check. Tables: Reservation, StorageUnit. | Medium | Khang | To Do |  | Core
FE-23 | Reservation Management | Reservation queue — UI | Facility Staff | Lists reservations by status with search by code, customer name, phone and move-in date. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-24 | Reservation Management | Assign unit — API | Facility Staff | Picks a concrete available unit for a reservation and holds it until the move-in date. ▸ Backend: endpoints, service logic, validation and role check. Tables: Reservation, StorageUnit. | Complex | Khang | To Do |  | Core
FE-24 | Reservation Management | Assign unit — UI | Facility Staff | Picks a concrete available unit for a reservation and holds it until the move-in date. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-25 | Reservation Management | Cancel / no-show — API | Facility Staff | Marks a reservation cancelled or no-show, releases the held unit and applies the deposit rule. ▸ Backend: endpoints, service logic, validation and role check. Tables: Reservation, StorageUnit. | Medium | Khang | To Do |  | Core
FE-25 | Reservation Management | Cancel / no-show — UI | Facility Staff | Marks a reservation cancelled or no-show, releases the held unit and applies the deposit rule. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-26 | My Contract | View contract — API | Storage Customer | Shows the contract terms, unit, monthly rent and period, and lets the customer download it as PDF. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract. | Medium | Nhân | To Do |  | Core
FE-26 | My Contract | View contract — UI | Storage Customer | Shows the contract terms, unit, monthly rent and period, and lets the customer download it as PDF. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-27 | My Contract | E-sign contract — API | Storage Customer | Captures the customer's signature on the contract and moves it from Draft to Signed. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract. | Complex | Nhân | To Do |  | Core
FE-27 | My Contract | E-sign contract — UI | Storage Customer | Captures the customer's signature on the contract and moves it from Draft to Signed. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Đạt | To Do |  | Core
BE-28 | Handover | Check-in checklist — API | Facility Staff | Step-by-step check-in: verify identity, confirm the signed contract, walk to the unit and inspect it. ▸ Backend: endpoints, service logic, validation and role check. Tables: Handover, Reservation, Contract, StorageUnit. | Complex | Khang | To Do |  | Core
FE-28 | Handover | Check-in checklist — UI | Facility Staff | Step-by-step check-in: verify identity, confirm the signed contract, walk to the unit and inspect it. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Thiện | To Do |  | Core
BE-29 | Handover | Capture handover evidence — API | Facility Staff | Records the lock serial number, the unit condition and photos taken at the moment of handover. ▸ Backend: endpoints, service logic, validation and role check. Tables: Handover, Reservation, Contract, StorageUnit. | Complex | Khang | To Do |  | Core
FE-29 | Handover | Capture handover evidence — UI | Facility Staff | Records the lock serial number, the unit condition and photos taken at the moment of handover. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Thiện | To Do |  | Core
BE-30 | Handover | Confirm handover — API | Facility Staff | Captures the customer and staff signatures, completes the handover and triggers contract activation. ▸ Backend: endpoints, service logic, validation and role check. Tables: Handover, Reservation, Contract, StorageUnit. | Complex | Khang | To Do |  | Core
FE-30 | Handover | Confirm handover — UI | Facility Staff | Captures the customer and staff signatures, completes the handover and triggers contract activation. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-31 | Contract Management | Contract list — API | Facility Manager | Lists contracts with unit, customer, period, monthly rent and status, with filters and export. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract, StorageUnit. | Medium | Nhân | To Do |  | Core
FE-31 | Contract Management | Contract list — UI | Facility Manager | Lists contracts with unit, customer, period, monthly rent and status, with filters and export. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-32 | Contract Management | Activate contract — API | Facility Staff | Turns a signed contract into an active rental after handover and marks the unit occupied. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract, StorageUnit. | Medium | Nhân | To Do |  | Core
FE-32 | Contract Management | Activate contract — UI | Facility Staff | Turns a signed contract into an active rental after handover and marks the unit occupied. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-33 | Contract Management | Terminate contract — API | Facility Manager | Ends a contract early or on move-out, frees the unit and closes any open access codes. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract, StorageUnit. | Medium | Nhân | To Do |  | Core
FE-33 | Contract Management | Terminate contract — UI | Facility Manager | Ends a contract early or on move-out, frees the unit and closes any open access codes. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-34 | Access Code Management | Issue access code — API | Facility Staff | Generates a gate and unit access code for an active contract with a validity window. ▸ Backend: endpoints, service logic, validation and role check. Tables: AccessCode, AccessLog. | Medium | Nhân | To Do |  | Core
FE-34 | Access Code Management | Issue access code — UI | Facility Staff | Generates a gate and unit access code for an active contract with a validity window. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-35 | Access Code Management | Revoke access code — API | Facility Staff | Deactivates a code on lockout, move-out or when the customer reports it lost. ▸ Backend: endpoints, service logic, validation and role check. Tables: AccessCode, AccessLog. | Simple | Nhân | To Do |  | Core
FE-35 | Access Code Management | Revoke access code — UI | Facility Staff | Deactivates a code on lockout, move-out or when the customer reports it lost. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Thiện | To Do |  | Core
BE-36 | Access Code Management | Access log viewer — API | Facility Manager | Searchable log of gate entries and exits by unit, customer and date range. ▸ Backend: endpoints, service logic, validation and role check. Tables: AccessCode, AccessLog. | Medium | Nhân | To Do |  | Core
FE-36 | Access Code Management | Access log viewer — UI | Facility Manager | Searchable log of gate entries and exits by unit, customer and date range. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-37 | Unit Access | Access code — API | Storage Customer | Shows the active gate and unit access code with its expiry time, and allows requesting a new one. ▸ Backend: endpoints, service logic, validation and role check. Tables: AccessCode, AccessLog. | Medium | Nhân | To Do |  | Core
FE-37 | Unit Access | Access code — UI | Storage Customer | Shows the active gate and unit access code with its expiry time, and allows requesting a new one. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-38 | Unit Access | Access history — API | Storage Customer | Lists the customer's own entries and exits with time and result. ▸ Backend: endpoints, service logic, validation and role check. Tables: AccessCode, AccessLog. | Simple | Nhân | To Do |  | Supporting
FE-38 | Unit Access | Access history — UI | Storage Customer | Lists the customer's own entries and exits with time and result. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-39 | Billing | Invoice list — API | Storage Customer | Lists the customer's invoices with billing period, amount, due date and status. ▸ Backend: endpoints, service logic, validation and role check. Tables: Invoice, InvoiceItem, Payment. | Medium | Trường | To Do |  | Core
FE-39 | Billing | Invoice list — UI | Storage Customer | Lists the customer's invoices with billing period, amount, due date and status. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-40 | Billing | Invoice detail — API | Storage Customer | Shows the line items of a single invoice, including rent, fees and any late charge. ▸ Backend: endpoints, service logic, validation and role check. Tables: Invoice, InvoiceItem, Payment. | Simple | Trường | To Do |  | Supporting
FE-40 | Billing | Invoice detail — UI | Storage Customer | Shows the line items of a single invoice, including rent, fees and any late charge. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-41 | Billing | Online payment — API | Storage Customer | Pays an outstanding invoice through the payment gateway and updates the invoice and contract status. ▸ Backend: endpoints, service logic, validation and role check. Tables: Invoice, InvoiceItem, Payment. | Complex | Trường | To Do |  | Core
FE-41 | Billing | Online payment — UI | Storage Customer | Pays an outstanding invoice through the payment gateway and updates the invoice and contract status. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Đạt | To Do |  | Core
BE-42 | Billing | Payment history — API | Storage Customer | Lists completed payments with method, amount, paid date and gateway reference. ▸ Backend: endpoints, service logic, validation and role check. Tables: Invoice, InvoiceItem, Payment. | Simple | Trường | To Do |  | Supporting
FE-42 | Billing | Payment history — UI | Storage Customer | Lists completed payments with method, amount, paid date and gateway reference. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-43 | Invoice & Payment | Generate monthly invoices — API | Business Operations Manager | Scheduled job that raises an invoice for every active contract at the start of each billing cycle. ▸ Backend: endpoints, service logic, validation and role check. Tables: Invoice, InvoiceItem, Payment. | Complex | Trường | To Do |  | Supporting
BE-44 | Invoice & Payment | Record manual payment — API | Facility Staff | Records a cash or bank transfer payment against an invoice and issues a receipt. ▸ Backend: endpoints, service logic, validation and role check. Tables: Invoice, InvoiceItem, Payment. | Medium | Trường | To Do |  | Core
FE-43 | Invoice & Payment | Record manual payment — UI | Facility Staff | Records a cash or bank transfer payment against an invoice and issues a receipt. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-45 | Invoice & Payment | Refund / adjustment — API | Business Operations Manager | Issues a refund or credit note against an invoice with a reason and approval. ▸ Backend: endpoints, service logic, validation and role check. Tables: Invoice, InvoiceItem, Payment. | Medium | Trường | To Do |  | Supporting
FE-44 | Invoice & Payment | Refund / adjustment — UI | Business Operations Manager | Issues a refund or credit note against an invoice with a reason and approval. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Supporting
BE-46 | Move-out | Move-out request — API | Storage Customer | Submits the planned move-out date and validates it against the notice period in the contract. ▸ Backend: endpoints, service logic, validation and role check. Tables: MoveOutRequest, ReturnInspection. | Medium | Nhân | To Do |  | Core
FE-45 | Move-out | Move-out request — UI | Storage Customer | Submits the planned move-out date and validates it against the notice period in the contract. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-47 | Move-out | Return inspection result — API | Storage Customer | Shows the inspection outcome, any damage note with photos, and the deposit amount to be refunded. ▸ Backend: endpoints, service logic, validation and role check. Tables: MoveOutRequest, ReturnInspection. | Medium | Nhân | To Do |  | Core
FE-46 | Move-out | Return inspection result — UI | Storage Customer | Shows the inspection outcome, any damage note with photos, and the deposit amount to be refunded. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Core
BE-48 | Move-out & Return | Move-out queue — API | Facility Staff | Lists approved move-out requests ordered by planned date, with the units to be inspected. ▸ Backend: endpoints, service logic, validation and role check. Tables: MoveOutRequest, ReturnInspection, Contract. | Medium | Nhân | To Do |  | Core
FE-47 | Move-out & Return | Move-out queue — UI | Facility Staff | Lists approved move-out requests ordered by planned date, with the units to be inspected. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
BE-49 | Move-out & Return | Return inspection form — API | Facility Staff | Records the unit condition, damage notes and photos when the unit is handed back. ▸ Backend: endpoints, service logic, validation and role check. Tables: MoveOutRequest, ReturnInspection, Contract. | Complex | Nhân | To Do |  | Core
FE-48 | Move-out & Return | Return inspection form — UI | Facility Staff | Records the unit condition, damage notes and photos when the unit is handed back. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Thiện | To Do |  | Core
BE-50 | Move-out & Return | Deposit settlement — API | Business Operations Manager | Calculates the refund after deducting damage and outstanding charges, then triggers the payout. ▸ Backend: endpoints, service logic, validation and role check. Tables: MoveOutRequest, ReturnInspection, Contract. | Complex | Nhân | To Do |  | Core
FE-49 | Move-out & Return | Deposit settlement — UI | Business Operations Manager | Calculates the refund after deducting damage and outstanding charges, then triggers the payout. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Core
FE-50 | Home | Landing page — UI | Storage Customer | Public home page with a hero search by district and unit size, plus highlighted facilities and how-it-works steps. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-51 | My Profile | Edit profile — API | Storage Customer | Updates the customer's name, phone number and address. ▸ Backend: endpoints, service logic, validation and role check. Tables: User. | Simple | Khang | To Do |  | Supporting
FE-51 | My Profile | Edit profile — UI | Storage Customer | Updates the customer's name, phone number and address. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-52 | My Profile | Change password — API | Storage Customer | Changes the password after confirming the current one. ▸ Backend: endpoints, service logic, validation and role check. Tables: User. | Simple | Khang | To Do |  | Supporting
FE-52 | My Profile | Change password — UI | Storage Customer | Changes the password after confirming the current one. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-53 | My Profile | Notification settings — API | Storage Customer | Chooses which reminders and confirmations arrive by email or SMS. ▸ Backend: endpoints, service logic, validation and role check. Tables: User. | Simple | Khang | To Do |  | Supporting
FE-53 | My Profile | Notification settings — UI | Storage Customer | Chooses which reminders and confirmations arrive by email or SMS. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-54 | Renewal | Request renewal — API | Storage Customer | Lets the customer extend the contract by a number of months and shows the resulting end date and new rent. ▸ Backend: endpoints, service logic, validation and role check. Tables: Renewal, Contract. | Medium | Nhân | To Do |  | Supporting
FE-54 | Renewal | Request renewal — UI | Storage Customer | Lets the customer extend the contract by a number of months and shows the resulting end date and new rent. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-55 | Renewal | Renewal status — API | Storage Customer | Shows whether the renewal request was approved and links to the updated contract. ▸ Backend: endpoints, service logic, validation and role check. Tables: Renewal, Contract. | Simple | Nhân | To Do |  | Supporting
FE-55 | Renewal | Renewal status — UI | Storage Customer | Shows whether the renewal request was approved and links to the updated contract. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Đạt | To Do |  | Supporting
BE-56 | Overdue Management | Overdue case list — API | Facility Manager | Lists overdue invoices grouped by stage and days overdue, with the accumulated late fee. ▸ Backend: endpoints, service logic, validation and role check. Tables: OverdueCase, Reminder, AccessCode. | Medium | Trường | To Do |  | Supporting
FE-56 | Overdue Management | Overdue case list — UI | Facility Manager | Lists overdue invoices grouped by stage and days overdue, with the accumulated late fee. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Supporting
BE-57 | Overdue Management | Reminder scheduling — API | Business Operations Manager | Sends payment reminders at configured intervals through email and SMS and logs the delivery result. ▸ Backend: endpoints, service logic, validation and role check. Tables: OverdueCase, Reminder, AccessCode. | Complex | Trường | To Do |  | Supporting
BE-58 | Overdue Management | Lockout action — API | Facility Manager | Suspends the access codes of a contract when its overdue case reaches the lockout stage. ▸ Backend: endpoints, service logic, validation and role check. Tables: OverdueCase, Reminder, AccessCode. | Complex | Trường | To Do |  | Supporting
FE-57 | Overdue Management | Lockout action — UI | Facility Manager | Suspends the access codes of a contract when its overdue case reaches the lockout stage. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Complex | Thiện | To Do |  | Supporting
BE-59 | Support | Create support ticket — API | Storage Customer | Raises a ticket against a rented unit with category, priority and description, with file attachments. ▸ Backend: endpoints, service logic, validation and role check. Tables: SupportTicket, TicketMessage, TicketCategory. | Medium | Nhân | To Do |  | Supporting
FE-58 | Support | Create support ticket — UI | Storage Customer | Raises a ticket against a rented unit with category, priority and description, with file attachments. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-60 | Support | Ticket conversation — API | Storage Customer | Message thread on one ticket between the customer and the assigned staff member. ▸ Backend: endpoints, service logic, validation and role check. Tables: SupportTicket, TicketMessage, TicketCategory. | Medium | Nhân | To Do |  | Supporting
FE-59 | Support | Ticket conversation — UI | Storage Customer | Message thread on one ticket between the customer and the assigned staff member. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-61 | Support & Maintenance | Ticket queue — API | Facility Staff | Lists support tickets by priority, category and status across the facilities the staff member covers. ▸ Backend: endpoints, service logic, validation and role check. Tables: SupportTicket, MaintenanceOrder. | Medium | Nhân | To Do |  | Supporting
FE-60 | Support & Maintenance | Ticket queue — UI | Facility Staff | Lists support tickets by priority, category and status across the facilities the staff member covers. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Supporting
BE-62 | Support & Maintenance | Assign ticket — API | Facility Manager | Assigns a ticket to a staff member and sets a due date, notifying the assignee. ▸ Backend: endpoints, service logic, validation and role check. Tables: SupportTicket, MaintenanceOrder. | Simple | Nhân | To Do |  | Supporting
FE-61 | Support & Maintenance | Assign ticket — UI | Facility Manager | Assigns a ticket to a staff member and sets a due date, notifying the assignee. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Simple | Thiện | To Do |  | Supporting
BE-63 | Support & Maintenance | Maintenance order — API | Facility Staff | Creates a maintenance order from a ticket and records the scheduled date, work done and cost. ▸ Backend: endpoints, service logic, validation and role check. Tables: SupportTicket, MaintenanceOrder. | Medium | Nhân | To Do |  | Supporting
FE-62 | Support & Maintenance | Maintenance order — UI | Facility Staff | Creates a maintenance order from a ticket and records the scheduled date, work done and cost. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Supporting
BE-64 | Staff Management | Staff account CRUD — API | System Administrator | Creates staff accounts, assigns roles and links each account to the facilities it may work at. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, StaffFacility, Shift, StaffTask. | Medium | Nhân | To Do |  | Supporting
FE-63 | Staff Management | Staff account CRUD — UI | System Administrator | Creates staff accounts, assigns roles and links each account to the facilities it may work at. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-65 | Staff Management | Shift scheduling — API | Facility Manager | Plans staff shifts per facility and date, preventing double booking. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, StaffFacility, Shift, StaffTask. | Medium | Nhân | To Do |  | Supporting
FE-64 | Staff Management | Shift scheduling — UI | Facility Manager | Plans staff shifts per facility and date, preventing double booking. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-66 | Staff Management | Task assignment — API | Facility Manager | Assigns tasks within a shift and tracks their completion. ▸ Backend: endpoints, service logic, validation and role check. Tables: User, StaffFacility, Shift, StaffTask. | Medium | Nhân | To Do |  | Supporting
FE-65 | Staff Management | Task assignment — UI | Facility Manager | Assigns tasks within a shift and tracks their completion. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-67 | Admin Dashboard | Dashboard KPIs — API | Facility Manager, Business Operations Manager | Occupancy rate, arrivals expected today, pending handovers, overdue cases and revenue for the month. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract, Invoice, StorageUnit. | Complex | Trường | To Do |  | Supporting
FE-66 | Admin Dashboard | Dashboard KPIs — UI | Facility Manager, Business Operations Manager | Occupancy rate, arrivals expected today, pending handovers, overdue cases and revenue for the month. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Thiện | To Do |  | Supporting
BE-68 | Reports | Occupancy report — API | Business Operations Manager | Occupancy by facility and unit type over a chosen period, with export to Excel. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract, Invoice, Payment, ActivityLog. | Complex | Trường | To Do |  | Supporting
FE-67 | Reports | Occupancy report — UI | Business Operations Manager | Occupancy by facility and unit type over a chosen period, with export to Excel. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-69 | Reports | Revenue report — API | Business Operations Manager | Revenue, outstanding amount and refunds by facility and month, with export to Excel. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract, Invoice, Payment, ActivityLog. | Complex | Trường | To Do |  | Supporting
FE-68 | Reports | Revenue report — UI | Business Operations Manager | Revenue, outstanding amount and refunds by facility and month, with export to Excel. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
BE-70 | Reports | Activity log — API | System Administrator | Audit trail of who changed what and when, filterable by user, action and date. ▸ Backend: endpoints, service logic, validation and role check. Tables: Contract, Invoice, Payment, ActivityLog. | Medium | Trường | To Do |  | Supporting
FE-69 | Reports | Activity log — UI | System Administrator | Audit trail of who changed what and when, filterable by user, action and date. ▸ Frontend: screen or section with loading, empty and error states; form rules mirror the API validator. | Medium | Đạt | To Do |  | Supporting
INT-01 | Integration | Auth end-to-end | All | Wire JWT issue → axios interceptor → role guards. Agree the claim names and the five role strings, then prove each role reaches only its own screens. | Complex | Khang + Đạt | To Do |  | Collab
INT-02 | Integration | API contract freeze | All | Walk the DTOs for the core flow together and freeze field names and the PagedResult shape before the frontend types are written. Record the result in docs/api-endpoints.md. | Medium | Khang + Nhân + Trường + Đạt + Thiện | To Do |  | Collab
INT-03 | Integration | CORS and environment config | All | API allows the Vite origin in Development; frontend reads VITE_API_BASE_URL. Verify a real request crosses from 5173 to 7001 with the bearer token attached. | Simple | Khang + Đạt | To Do |  | Collab
INT-04 | Integration | Payment gateway sandbox | Storage Customer | Connect the sandbox, agree the callback contract, and handle success, failure and timeout on both sides for the deposit and for an invoice. | Complex | Trường + Đạt | To Do |  | Collab
INT-05 | Integration | Core flow end-to-end run | All | One unit travels Available → Reserved → Signed → Occupied → billed → Available across both apps, with no manual database edits. This is the demo path. | Complex | Khang + Nhân + Trường + Thiện | To Do |  | Collab
INT-06 | Integration | Seed and demo dataset | System Administrator | Seed roles, two facilities with floors and units, unit types, one active pricing policy and a set of demo accounts, so any teammate can run the flow from a clean database. | Medium | Khang + Trường | To Do |  | Collab
INT-07 | Integration | Deployment | All | Publish the API and the built SPA, with connection string and JWT key supplied as environment variables, never committed. | Complex | Khang + Thiện | To Do |  | Collab
INT-08 | Integration | Demo rehearsal and report figures | All | Run the presentation path twice, capture the screenshots and numbers the report needs, and fix whatever breaks. | Medium | Khang + Nhân + Trường + Đạt + Thiện | To Do |  | Collab

## Modules
Module ownership — one backend owner and one frontend owner per module
# | Module | Backend owner | Frontend owner | Features | BE points | FE points | Priority
1 | Register / Login | Khang | Đạt | 4 | 7 | 7 | Core
2 | Admin Login | Khang | Thiện | 1 | 2 | 2 | Core
3 | Facility Search | Khang | Đạt | 2 | 4 | 4 | Core
4 | Unit Catalog | Trường | Đạt | 3 | 7 | 5 | Core
5 | Unit Type & Pricing | Trường | Thiện | 4 | 8 | 7 | Core
6 | Facility Management | Khang | Thiện | 4 | 8 | 7 | Core
7 | Reservation | Khang | Đạt | 4 | 9 | 9 | Core
8 | Reservation Management | Khang | Thiện | 3 | 7 | 6 | Core
9 | My Contract | Nhân | Đạt | 2 | 5 | 5 | Core
10 | Handover | Khang | Thiện | 3 | 9 | 8 | Core
11 | Contract Management | Nhân | Thiện | 3 | 6 | 6 | Core
12 | Access Code Management | Nhân | Thiện | 3 | 5 | 5 | Core
13 | Unit Access | Nhân | Đạt | 2 | 3 | 3 | Core
14 | Billing | Trường | Đạt | 4 | 7 | 7 | Core
15 | Invoice & Payment | Trường | Thiện | 3 | 7 | 4 | Core
16 | Move-out | Nhân | Đạt | 2 | 4 | 4 | Core
17 | Move-out & Return | Nhân | Thiện | 3 | 8 | 7 | Core
18 | Home | — | Đạt | 1 | 0 | 1 | Supporting
19 | My Profile | Khang | Đạt | 3 | 3 | 3 | Supporting
20 | Renewal | Nhân | Đạt | 2 | 3 | 3 | Supporting
21 | Overdue Management | Trường | Thiện | 3 | 8 | 5 | Supporting
22 | Support | Nhân | Đạt | 2 | 4 | 4 | Supporting
23 | Support & Maintenance | Nhân | Thiện | 3 | 5 | 5 | Supporting
24 | Staff Management | Nhân | Đạt | 3 | 6 | 6 | Supporting
25 | Admin Dashboard | Trường | Thiện | 1 | 3 | 2 | Supporting
26 | Reports | Trường | Đạt | 3 | 8 | 6 | Supporting
| Total |  |  | 71 | 146 | 131